PNAMP: Quarterly Status Brief

# January – March 2026

# Coordination: Steering Committee Meeting Series

Completed

- Conduct survey of PNAMP impacts to inform 2027 work plan and accomplishments tracking

- Engaged in one-on-one meetings with steering committee members to obtain ideas on refreshing the roles and responsibilities of the SC members

- Drafted the 2025 Annual Report. The first draft is complete and under review by the Steering Committee and other assigned reviewers

In Progress

- Planning PNAMP Steering Committee Special Session Meeting scheduled for April 16th

- Summarize input received from PNAMP Refresh planning survey and one-on-one, and develop recommendations to inform FY27

- Finalizing the 2025 PNAMP Annual Report

Issues

- N/A

# Coordination: CRBRP Toxics Monitoring Subgroup (TMS)

Completed

- The Toxics Monitoring Subgroup has been moved from PNAMP to EPA

# Coordination: Emerging Technologies Information Sessions

Completed

- Created the ETIS Invitation and sent it out to past participants

- Updated the ETIS webpage

- Finalized the 2026 ETIS Logo and the ETIS theme

- Sent a “save the date” and the ETIS Invitation in the February and March PNAMP Newsletters

- Held three ETIS Planning Committee meetings

- Finalized the ETIS abstract submission form

- Presented ETIS at SN SC meeting and SN TT/DDT(s) Meeting

In Progress

- Secure all sponsors and exhibitors

- Call for Abstracts in the PNAMP April Newsletter

- Finalize venue, food, space

- Review abstracts

- Set up C-Vent registration (no fee reg, fee reg, food selection)

- Open Registration

- Create agenda and add it to the website and C-Vent registration

- Host Event - end of Oct 26-28, 2026

Issues

- N/A

# Coordination: Fish Monitoring Work Group

Completed

- On January 15, 2026, the FMWG convened for updates on tasks and a Tech Talk from Greg Wilke (PSMFC) and Kris Warner (WDFW) on the Regional Mark Inventory System (RMIS) R package. R package users showcased coding their workflows, and a discussion on desired improvements and ways to enhance usability. From Data to Decisions: RMIS in R at Your Fingertips – Explore how RMIS and R work together to transform raw data into meaningful fisheries management decisions. (meeting recording)

- A summary was completed in January for Update Terms and Definitions Used in CAP Data Standards task (link)

- The FMWG Core Team met in January, February, and March to plan and coordinate future work, discuss task progress and potential presenter for the April 2026 meeting.

In Progress

- Planning for the April FMWG meeting is under development.

- Carrying Capacity paper is under peer review and will be submitted to journals in the coming quarter.

- RST now Juvenile Fish Trap Discovery Tool and development is being coordinated through the StreamNet Tech Team

- “One Stop Resource” page for PIT tag data and analysis is under development

- Upcoming tasks are launching: Genetics: one task on PBT and the other on eDNA; Focal Species Polygons

# Coordination: Effectiveness Monitoring (Intensively Monitored Watersheds Forum)

Completed

- Submitted proposal to host a symposium at the joint Oregon and Western Division American Fisheries Society (AFS) Meeting - “Transforming Effectiveness Monitoring in the Pacific Northwest”

- Reached out to potential presenters and panel members for the AFS symposium

In Progress

- Preparing for the Effectiveness Monitoring symposium at Western Division AFS

Issues

- Looking to hire someone to fill the role of the Effectiveness Monitoring Task lead

# User Support: MonitoringResources.org

Completed

- QA/QC: Reviewed provided feedback, and finalized 6 protocols from Jan 1st – Mar 31st, 2026

- QA/QC: Reviewed provided feedback, and finalized 8 methods from Jan 1st – Mar 31st, 2026

- Displayed 50 new data collection events (sites) to the Explorer map  from Jan 1st – Mar 31st, 2026

- Identified 48 projects that are past due or nearing their contract end date

  - Reached out to 12 Project sponsors to assist them in completing their contractually required projects in Monitoring Resources

- Provided one-to-one guidance and assistance to MonitoringResources.org users at NOAA, BPA, MFWP, ODFW, and WDFW

- Presented at the SN SC Meeting

- Wrote an Abstract for the Western Division AFS meeting

In Progress

- Reaching out to the remaining 36 project sponsors to assist them in finalizing the Monitoring Resources documentation

  - Continue to provide one-to-one guidance to any other project sponsor who may request help

- Reviewing and approving content documented in Monitoring Resources as needed

- Updating guidance documents and the Monitoring Resources FAQ page

- Creating a digital Fish ID and condition field guide in conjunction with BPA, ODFW, and CBF&WL

- Conduct annual survey to determine how MonitoringResources.org is used/who is using it

Issues

- How do we simplify the process for users to enter information in MonitoringResources.org?

# Data Management: MonitoringResources.org

Completed

- Changed ownership from the individual level to the organizational level

- Made the Metrics & indicators subcategory focus 1 and subcategory focus 2 optional

- Updated the level of Zoom in the Area of Inference (AOI) map on Study Plan Summary to get a better view of the AOI

- Provided the capability to version a Study Plan from the Study Plan Summary page

- Fixed a bug when editing metric and indicator sub-categories

- Met bi-weekly with ESA and BPA to determine next/best developments to Monitoring Resources

  - Regularly tested Monitoring Resources development to ensure it was working appropriately

In Progress

- Providing the ability to add secondary authors to Monitoring Resources documentation

- Use machine learning to populate metrics and indicators from an uploaded or scanned data sheet

- Add polygon focal species layer to Monitoring Explorer this will connect to SN and CBFish - polygons on the HUC level, tell you what species are present

- Add Columbia Basin Fish Facilities Layer to Monitoring Explorer and the Sample Designer map

- Backend development needed to keep up with CBFish upgrades

Issues

- How do we link the Study Plan Summary to other regional data systems?

- Documenting existing and established methods not yet present in MonitoringResources.org

# Communication

Completed

- Completed the January, February, and March PNAMP newsletters

- Posted 14 new announcements to PNAMP.org from Jan 1st – Mar 31st, 2026

- Regularly posted and updated “Upcoming Events” on PNAMP.org

In Progress

- Maintaining PNAMP.org including updating Events, adding Announcements, and posting Newsletters

- Developing the April, May, and June Newsletter

- Maintain PNAP membership database

- Support Salmon Data Mobilization

Issues

- N/A

# Website

Completed

- Updated the ETIS Project page

- Updated the About - Leadership page

In Progress

- Maintaining PNAMP.org including updating Events, adding Announcements, and posting Newsletters

- Maintaining ADA compliance

Issues

- Need to transition from the GreenGeeks server to the PSMFC server