# PNAMP Quarterly Status Report              January – March 2025

# Coordinated Assessments Partnership & HCAX Project

Accomplishments

- Facilitated two workshops the 2025 WA/BC American Fisheries Chapter Meeting in Vancouver British Columbia :(March 9th 2025). More than 55 people joined our salmon data mobilization workshop and over 30 joined the workshop/training on the HCAX data via Coordinated Assessments system at StreamNet

- Facilitated the CAP Core Team standing meetings, resulting in progress on coordination for data sharing across partners, with emphasis on BPA funded projects

- Participated in and provided support for StreamNet Steering Committee meeting; including tasks support for dashboards and focal species work to enhance data delivery at StreamNet

In Progress

- Advance the “Update CAP Terms and Definitions” task, by completing the review of recommendations for needed changes and devising a plan to implement these changes with StreamNet partners

- Supported the development of a "best practices for salmon data mobilization" manuscript for peer review publication

# Coordination and Communication

Accomplishments

- Provided review and feedback to the Salmon Climate Initiative and the Basin Effects and Coastal Impacts initiative.

- Completed the January, February, and March PNAMP newsletters

In Progress

- Maintaining PNAMP.org including updating Events, adding Announcements, and posting Newsletters

- Developing the April, May, and June Newsletter

# CRBRP Toxics Monitoring Subgroup (TMS)

Accomplishments

- Participated in EPA CRBRP in person retreat to develop a science and monitoring strategy for the Columbia Basin

- Supported EPA CRBRP in developing an engagement strategy for the science and monitoring strategy for the Columbia Basin and implementation of this engagement strategy to gather input from interested parties

- Facilitated the CRBRP TMS meeting February 11, 2025, which included: two presentations centered around data management – one by Edyth Hermosillo (EPA) on the importance of data management, the second by Chris Neumiller (WA Ecology) on insights from 25 years of Environmental Data Management at WA Ecology. The meeting also included a partner round robin and updates from the TMS Core Team. Meeting slide deck here.

In Progress

- Preparing for the June 10 TMS workshop.

# Emerging Technologies Information Sessions

Accomplishments

- Hosted and facilitated five, two-hour webinar sessions from January 8 – February 5, 2025

  - Modeling and Analysis, Artificial Intelligence and Machine Learning, Data QA/QC, Genetics, and Remote Sensing

  - More than 150 attended the series virtually

  - More than 550 YouTube views

- Published announcements in the January and February Newsletter

- Published a wrap-up article in the March newsletter

- Created and sent out a survey to ETIS participants

In Progress

- Preparing for the Fall/Winter 2026 ETIS Hybrid event

# Fish Monitoring Work Group

Accomplishments

- On January 16, 2025, the full work group convened for updates on tasks and a Tech Talk from Russell Perry, a Research Fish Biologist in the Quantitative Ecology Section at the US Geological Survey presented Putting Time Back into Space-for-Time Mark-Recapture Models. In this presentation, he described Time-Integrated Migration and Survival (TIMS) models that overcome this limitation of space-for-time mark-recapture models. TIMS models combine a migration model with a mark-recapture model to explicitly model travel times between detection gates and to account for probable arrival times and environmental conditions experienced by undetected fish. (Meeting recording available by request only)

- The FMWG Core Team met in January, February, and March to plan and coordinate future work, discuss task progress and potential presenter for the April 2025 meeting.

- Planning for a 2025 PIT Tag data webinar series has identified topics and potential speakers, details have been announced to the FMWG, CAP, and PNAMP distribution lists. The webinar Series will begin on April 24th, 2025.

In Progress

- Final details for the 2025 PIT Tag data webinar series are being wrapped up and presenters are preparing and submitting information for their presentations.

- Planning for the October FMWG meeting is under development.

- Carrying Capacity paper is under review from section authors, and the discussion section is being refined.

# Intensively Monitored Watersheds Forum

Accomplishments

- PNAMP convened a planning group on Feb 6th to continue discussing ideas for a workshop/workshop series to develop a vision for what’s next for large-scale effectiveness monitoring.

# MonitoringResources.org

Accomplishments

- Reviewed and provided feedback on 20 protocols, and finalized 17 protocols from Jan 1st – Mar 31st, 2024

- Reviewed and provided feedback on 39 methods, and finalized 32 methods from Jan 1st – Mar 31st, 2024

- Updated the Validation of Data Collection Events tutorial

- Finalized development work on updates to the “User Interface”

  - Ensure all Tiny MCE characters (Rich Text Editor) save, display and load correctly

  - SPIKE - RCA for Tiny MCE special characters display

  - Add Superscript and Subscript options to Tiny MCE

  - Add help text telling users to fill in metrics before methods in BPA Workflow

- Finalized development work on updates to the “Data Collection Event Map”

  - Ability to highlight a pin when clicking a row, and vice-versa

- Finalized development work on updates to "Adding Focal Species”

  - Add Focal Species support request type

  - Add Focal Species metric to Sample Design, sample design grids, and summary page

  - Add Focal Species to Sample Design editor

  - Focal Species Admin page

- Coordinated biweekly meetings with ESA Sitka to discuss current and future development

- Coordinated meetings with BPA to ensure development was on schedule and appropriate fixes were being addressed

- Provided one-to-one guidance and assistance to MonitoringResources.org users at OWEB, IDFG, PSMFC, ODFW, Michigan State University, Spokane Tribe, and NOAA

In Progress

- Developing a better interface and data stream between GitHub/GitLab and Monitoring Resources

- Assisting project sponsors interested in MonitoringResources.org guidance with one-to-one webinar sessions

- Developing a clearer association between methods and metrics and using these metric associations to assist with metadata discover via cluster models and key word search

- Assist in uploading or “validating” data collection events to provide greater metadata discovery on the Monitoring Resources' Explorer Map

- Creating a more user-friendly Data Collection Event Map with better search functionality

- Updating layers in MonitoringResources.org and the Data Collection Event Map to align with StreamNet and NPCC

- Creating a tutorial video on how to validate actual sampling locations

- Creating a help video on how to copy/paste equations and special characters from GitHub into Monitoring Resources.

- Investigating connections between MonitoringResources.org and the Salmon Data Discovery Tool and SalHub

- Exploring the creation and use of ontologies

Outstanding Issues

- How do we link the Study Plan Summary to other regional data systems?

- Documenting existing and established methods not yet present in MonitoringResources.org

- How do we simplify the process for users to enter information in MonitoringResources.org?

# Steering Committee Meeting Series

Accomplishments

- Draft Annual Report is complete and under review by the Steering Committee and other assigned reviewers

In Progress

- Planning for the May 7th PNAMP Steering Committee Meeting has been initiated. The half-day hybrid format will address accomplishments during 2024 and planned work for 2025 and 2026.